## Product Backlog
Product Name: | JADE Manager | [5 empty] | Complete Fields in Green!!!
Team ID: | Waseem Alkasbutrus
| Team Member Name |  |  |  |  | Initials | Student ID
Required | Waseem Alkasbutrus |  |  |  |  | WIA | 1001841927
Updated for Sprint 4
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 36 |  |  | Total | Total number of features (in column H)
1 | 33 | 3 |  | 1 | Total features left at the end of Sprint #1
2 | 31 | 2 |  | 2 | Total features left at the end of Sprint #2
3 | 26 | 5 |  | 3 | ...and so on
4 | 25 | 1
5 | 18 | 7
6 | 18 | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
|  |  |  | Sprints |  | Features are always graded at the end of the sprint in which they are required, regardless of when they are implemented
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Create a new coffee flavor | Stock and sell coffee products
CC | 2 | 1 | 5 | 1 | Finished in Sprint 1 | Manager | Create a new donut | Stock and sell donuts
STOR | 3 | 1 | 13 | 1 | Finished in Sprint 1 | Manager | Manage a list of coffee and donut products per store | Manage training and advertising
GUI | 4 | 2 | 8 | 2 | Finished in Sprint 2 | Manager | Use a main window (GUI) with simple menu bar tool bar | Reduce training costs | This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
IGUI | 5 | 2 | 21 | 2 | Finished in Sprint 2 | Manager | Use dialogs to create new coffee and donut products | Reduce training costs | Sequence of dialogs OK for initial prototype. One dialog each for coffee and for donuts is below.
CE | 6 | 3 | 13 | 3 | Finished in Sprint 3 | Manager | Create a new store | Franchise JADE operations | This includes all data in a store, including new features implemented in later sprints
SAVD | 7 | 3 | 8 | 3 | Finished in Sprint 3 | Manager | Save all data to a default file on exit or command | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
LOAD | 8 | 3 | 5 | 3 | Finished in Sprint 3 | Manager | Load data from a default file on startup | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
SALL | 9 | 3 | 5 | 3 | Finished in Sprint 3 | Owner | Save all data to a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
LALL | 10 | 3 | 5 | 3 | Finished in Sprint 3 | Owner | Load data from a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
UD | 11 | 4 | 21 | 4 | Finished in Sprint 5 | Manager | Create unified dialogs across the application | Interact more efficiently with the program | Each command (e.g., Create > Donut) should required a single dialog
CB | 12 | 4 | 8 | 4 | Finished in Sprint 4 | Server | Create a new beloved customer | Keep track of our customers
CS | 13 | 5 | 3 | 5 | Finished in Sprint 5 | Server | Create a new named server | Track server productivity and tips
CO | 14 | 5 | 8 | 5 | Finished in Sprint 5 | Server | Create an order of multiple products | Serve everyone in a customer party | Use a HashMap with Product index and int quantity value
PS | 15 | 5 | 5 | 5 | Finished in Sprint 5 | Customer | List all coffee and donut products in a dialog | See what the Customer can order | This is probably a combobox of each Product’s toString
POC | 16 | 5 | 3 | 5 | Finished in Sprint 5 | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB | 17 | 5 | 8 | 5 | Finished in Sprint 5 | Customer | Associate the order with a customer | Self-order and not have to deal with people | “What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CSS | 18 | 5 | 2 | 5 | Finished in Sprint 5 | Customer | Associate the order with a server | Order via a server so that they receive credit | “What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
P&L | 19 | 6 | 8 |  |  | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy | Demonstrate the use of Java iterators with this feature
RTM | 20 | 6 | 8 |  |  | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members | Demonstrate the use of Java iterators with this feature
EF | 21 | 6 | 8 |  |  | Manager | Edit a product | Improve our data and keep it synced to reality
The Features below are BONUS work. If implemented, they will be graded, and the bonus awarded, at the end of Sprint 6
|  | Bonus |  |  |  | (If a Bonus feature changes AFTER you have implemented it, please notify the Professor ASAP)
PIX | 22 | 50 | 21 |  |  | Customer | Add and display pictures for each item | Better understand the menu | Pics would be added on product creation, and displayed when composing a new order
CM | 23 | 5 | 3 |  |  | Owner | Create a new manager | Delegate management tasks to a pro
ASTO | 24 | 15 | 8 |  |  | Manager | Also associate a server with the order they fill | Keep track of our employee productivity
XT | 25 | 25 | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order, but keep their historical data) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 26 | 10 | 5 |  |  | Manager | Restore a server | Add a former team member tack into service
TIPS | 27 | 15 | 8 |  |  | Server | Calculate a percentage of each order served and report on each Server’s tips | Pay tip income as well as salary to Servers
AI | 28 | 15 | 8 |  |  | Server | Restock donuts and coffees | Ensure we can fill every order
MST | 29 | 10 | 5 |  |  | Manager | Manage the state of each order (unfilled -> filled and unpaid -> paid,, or unfilled / unpaid -> canceled) | Ensure each order is filled and payment collected | This is a good bonus problem if you attend the (optional) Lecture 24 on state machines
POS | 30 | 10 | 5 |  |  | Server | Show the products in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
RI | 31 | 10 | 5 |  |  | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
RO | 32 | 15 | 8 |  |  | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 33 | 10 | 5 |  |  | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
ROA | 34 | 5 | 3 |  |  | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
CENEW | 35 | 25 | 13 |  |  | Owner | Create a new franchise | Franchise my company
XI | 36 | 50 | 21 |  |  | Manager | Retire a product (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2021-10-05 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-12
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 13
Day 1 Left | 13 | 0
Day 2 Left | 13 | 0
Day 3 Left | 13 | 0
Day 4 Left | 13 | 0
Day 5 Left | 6 | 7
Day 6 Left | 0 | 6
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CF | WIA | Create a Java (coffee) class | Completed Day 5
2 | CF | WIA | create the darkness and shots enums | Completed Day 5
3 | CF | WIA | create darkness and shots attributes | Completed Day 5
4 | CF | WIA | create aeddShot method that adds a shot to the shots ArrayList | Completed Day 5
5 | CF | WIA | override toString method to print the donut name and customizations | Completed Day 6
6 | CC | WIA | Create a Donut class | Completed Day 5
7 | CC | WIA | create the frosting, and filling enums | Completed Day 5
8 | CC | WIA | create filling, frosting, and sprinkles attributes | Completed Day 5
9 | CC | WIA | override toString method to print the donut name and customizations | Completed Day 6
10 | STOR | WIA | Create the store class | Completed Day 6
11 | STOR | WIA | of items in products ArrayList | Completed Day 6
12 | STOR | WIA | create toString method that prints a single product's information | Completed Day 6
13 | STOR | WIA | override toString method of the class to print all the items in the store | Completed Day 6
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2021-10-12 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-19
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 12
Day 1 Left | 12 | 0
Day 2 Left | 10 | 2
Day 3 Left | 6 | 4
Day 4 Left | 4 | 2
Day 5 Left | 2 | 2
Day 6 Left | 0 | 2
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | GUI | WIA | Reorganizing Files into packages | Completed Day 2
2 | GUI | WIA | Creating MainWin class | Completed Day 3 | The class responsible for the main window of the program
3 | GUI | WIA | Creating a menubar object | Completed Day 3
4 | GUI | WIA | Creating menus and menu items to the menu bar | Completed Day 3
5 | GUI | WIA | Creating action listeners and methods for the menu items | Completed Day 4
6 | GUI | WIA | Creating button art | Completed Day 2 | Creating Button pictures using Aseprite pixel art program
7 | GUI | WIA | Creating buttons and their action listeners | Completed Day 3
8 | IGUI | WIA | Creating input dialogs for Java and Donut name, price, and cost | Completed Day 4
9 | IGUI | WIA | Create input dialogs with combo boxed for donut and java customizations | Completed Day 5 | to select Filling, Frosting, Darkness
10 | GUI | WIA | Display all products in the store to the screen | Completed Day 6
11 | IGUI | WIA | Create a confirm dialog to ask if the donut has sprinkles or not | Completed Day 5 | Only display this option if the donut has frosting
12 | IGUI | WIA | Create an about dialog with the logo, prgram version and copyright, along with appropriate creditation | Completed Day 6
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2021-10-19 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-10-26
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 20
Day 1 Left | 16 | 4
Day 2 Left | 11 | 5
Day 3 Left | 11 | 0
Day 4 Left | 11 | 0
Day 5 Left | 11 | 0
Day 6 Left | 8 | 3
Day 7 Left | 0 | 8
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CE | WIA | Create a "New" menuItem under file | Completed Day 1
2 | CE | WIA | Create a "New" button in the toolbar | Completed Day 2
3 | CE | WIA | Create a onNewClick method that will be called when new button and menu option are clicked | Completed Day 2
4 | SAVD | WIA | Create a save menuitem under file menu | Completed Day 1
5 | SAVD | WIA | Create a save button in the toolbar | Completed Day 2
6 | SAVD | WIA | create a onSaveClick to be called when save is clicked | Completed Day 6
7 | LALL | WIA | Create an Open menu item under file | Completed Day 1
8 | LALL | WIA | create an Open button in the toolbar | Completed Day 2
9 | LALL | WIA | create a onOpenClick method to be called when Open is clicked | Completed Day 6
10 | SALL | WIA | Create a Save As opetion under the file menu | Completed Day 1
11 | SALL | WIA | Create a Save As button in the toolbar | Completed Day 2
12 | SALL | WIA | Create a onSaveAsClick method to be called when save as is clicked | Completed Day 6
13 | SAVD | WIA | Create a save mothod for the store class | Completed Day 7
14 | LOAD | WIA | Create a Store constructor with a bufferedReader parameter | Completed Day 7
15 | SAVD | WIA | Create a save method for the Product class | Completed Day 7
16 | LOAD | WIA | Create a Product constructor with a bufferedReader parameter | Completed Day 7
17 | SAVD | WIA | Create a save method for the Donut class | Completed Day 7
18 | LOAD | WIA | Create a Donut constructor with a bufferedReader parameter | Completed Day 7
19 | SAVD | WIA | Create a save method for the Java class | Completed Day 7
20 | LOAD | WIA | Create a Java constructor with a bufferedReader parameter | Completed Day 7
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-02 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-11-09
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 28
Day 1 Left | 28 | 0
Day 2 Left | 15 | 13
Day 3 Left | 11 | 4
Day 4 Left | 7 | 4
Day 5 Left | 7 | 0
Day 6 Left | 0 | 7
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CB |  | Create Person.java | Completed Day 2
2 | CB |  | Write Person(String name, String phone) | Completed Day 2
3 | CB |  | Write Person(BufferedReader bufferedReader) | Completed Day 2
4 | CB |  | Write Person.save(BufferedReader bufferedReader) | Completed Day 2
5 | CB |  | Override Person.toString() | Completed Day 2
6 | CB |  | Create Customer.java | Completed Day 2
7 | CB |  | Write Customer(String name, String phone) | Completed Day 2
8 | CB |  | Write Customer(BufferedReader bufferedReader) | Completed Day 2
9 | CB |  | Override Customer.toString() | Completed Day 2
10 | CB |  | Add people array list to store.java | Completed Day 2
11 | CB |  | Implement Store.addPerson | Completed Day 2
12 | CB |  | Implement Store.numberOfPeople | Completed Day 2
13 | CB |  | Implement Store.personToString | Completed Day 2
14 | CB |  | Implement Store.peopleToString | Completed Day 3
15 | CB |  | Add View menu to menu bar | Completed Day 3
16 | CB |  | Add People menu item to view | Completed Day 3
17 | CB |  | Add Products menu item to view | Completed Day 3
18 | CB |  | Add People button to toolbar | Completed Day 6
19 | CB |  | Add Products button to toolbar | Completed Day 6
20 | CB |  | Implement MainWin.onPeopleClick Actionlistener | Completed Day 4
21 | CB |  | Implement MainWin.onProductsClick Actionlistener | Completed Day 4
22 | CB |  | Add Customer menu item to Create | Completed Day 4
23 | CB |  | Add Customer button to toolbar | Completed Day 6
24 | CB |  | Implement MainWin.onCreateCustomerClick Actionlistener | Completed Day 4
25 | UD |  | Create Components array for new donut | Completed Day 6
26 | UD |  | ShowConfirmDialog with array of components to add donut | Completed Day 6
27 | UD |  | Create Components array for new java | Completed Day 6
28 | UD |  | ShowConfirmDialog with array of components to add java | Completed Day 6
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-09 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-11-16
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 43
Day 1 Left | 41 | 2
Day 2 Left | 39 | 2
Day 3 Left | 32 | 7
Day 4 Left | 32 | 0
Day 5 Left | 31 | 1
Day 6 Left | 31 | 0
Day 7 Left | 31 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | UD |  | Implement adding shots int the new java unified dialog | Completed Day 3
2 | CS |  | Create a Server class | Completed Day 1
3 | CS |  | Create a constructor with name, phone, and parameters | Completed Day 1
4 | CS |  | Create a constructor with a buffered reader | Completed Day 3
5 | CS |  | Override the save method | Completed Day 3
6 | CS |  | Override the toString method | Completed Day 3
7 | CS |  | implement getSSN method | Completed Day 5
8 | CS |  | Create > Server in MainWin | Completed Day 2
9 | CS |  | Implement onCreateServerClick | Completed Day 2
10 | CO |  | Override euqals method for Product, Donut, and Java
11 | CO |  | Override hashCode method for Product, Donut, and Java
12 | CO |  | Create Order class with nextID(static), id, customer, server, products
13 | CO |  | Create a constructor customer and server
14 | CO |  | implement getID method
15 | CO |  | Implement addProduct method to add a product to products hashmap
16 | CO |  | override save method
17 | CO |  | override toString method
18 | CO |  | Add orders ArrayList to Store.java
19 | CO |  | update BufferedReader constructor to read orders from file
20 | CO |  | update save method to write orders to file
21 | CO |  | addOrder method that adds an order to store
22 | CO |  | numberOfOrders method that returns the number of orders
23 | CO |  | orderToString that returns a string representation of a given order
24 | CO |  | getOrders that returns an array of orders
25 | CO |  | ordersToString that returns a string representation of all orders in the store
26 | CO |  | Create > Order in MainWin
27 | CO |  | Create order button to toolbar MainWin
28 | CO |  | Implement onCreateOrderClick | Completed Day 3
29 | CO |  | View > Orders in MainWin
30 | CO |  | View Orders button to toolbar in MainWin
31 | CO |  | Implement viewing orders using updateData method | Completed Day 3
32 | CS |  | Used JFormattedTextField to perform data validation on all phone numbers and ssn | Completed Day 3
33 | POC |  | JLabel in creae order dialog
34 | PS |  | Store.getProduct method returns an aray of products
35 | PS |  | combo box with available products in new order dialog
36 | PS |  | spinner to select product quantity in new order dialog
37 | PS |  | button to add the product to the order in new order dialog
38 | PS |  | scroll pane to contain the order label
39 | PS |  | panel containing the combo box, spinner, and button above in new order dialog
40 | CSB |  | Store.getCustomers that returns array of customers
41 | CSB |  | combo box with added customers
42 |  |  | Store.getServers that returns array of Servers (Can't select CSS on dropdown)
43 |  |  | combo box with added servers (Can't select CSS on dropdown)
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2021-11-30 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2021-12-07 |  | NOTE: A stand-alone assignment on threading is Nov 16-30
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## 1-3 Product Backlog
Product Name: | JADE Manager | [5 empty] | Complete Fields in Green!!!
Team ID:
| Team Member Name |  |  |  |  | Initials | Student ID
Required
Sprint # | Remaining | Completed This Sprint |  |  | Comment
0 | 35 |  |  | Total | Total number of features (in column H)
1 | 35 | 0 |  | 1 | Total features left at the end of Sprint #1
2 | 35 | 0 |  | 2 | Total features left at the end of Sprint #2
3 | 35 | 0 |  | 3 | ...and so on
4 | 35 | 0
5 | 35 | 0
6 | 35 | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
|  |  |  | Sprints |  | Features are always graded at the end of the sprint in which they are required, regardless of when they are implemented
Feature ID | Priority | Required | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 | 13 |  |  | Manager | Create a new coffee flavor | Stock and sell coffee products
CC | 2 | 1 | 5 |  |  | Manager | Create a new donut | Stock and sell donuts
STOR | 3 | 1 | 13 |  |  | Manager | Manage a list of coffee and donut products per store | Manage training and advertising
GUI | 4 | 2 | 8 |  |  | Manager | Use a main window (GUI) with simple menu bar tool bar | Reduce training costs | This is the main window, with just a menu bar (for now). For this sprint, you can just hard-code or randomly create java and donuts
IGUI | 5 | 2 | 21 |  |  | Manager | Use dialogs to create new coffee and donut products | Reduce training costs | Sequence of dialogs OK for initial prototype. One dialog each for coffee and for donuts is below.
CE | 6 | 3 | 13 |  |  | Manager | Create a new store | Franchise JADE operations | This includes all data in a store, including new features implemented in later sprints
SAVD | 7 | 3 | 8 |  |  | Manager | Save all data to a default file on exit or command | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
LOAD | 8 | 3 | 5 |  |  | Manager | Load data from a default file on startup | Ensure our data isn’t lost | This includes all data in a store, including new features implemented in later sprints
SALL | 9 | 3 | 5 |  |  | Owner | Save all data to a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
LALL | 10 | 3 | 5 |  |  | Owner | Load data from a specified file | Franchise my company | Use the File Chooser dialog (see Lecture 15)
PS | 11 | 4 | 5 |  |  | Customer | List all coffee and donut products in a dialog | See what is available (and later, see what the Customer can order) | This is effectively a toString to a dialog with an OK button
CB | 12 | 4 | 2 |  |  | Server | Create a new beloved customer | Keep track of our customers
CO | 13 | 4 | 8 |  |  | Server | Create an order of multiple products | Serve everyone in a customer party
POC | 14 | 4 | 3 |  |  | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to and maybe identical to Feature PS
CSB | 15 | 4 | 8 |  |  | Customer | Associate the order with a customer | Self-order and not have to deal with people | “What name should I put on the ticket” so they can call for you when your order is ready. This also practices Map.
CS | 16 | 5 | 5 |  |  | Server | Create a new named server and associate with orders | Track server productivity and tips
CM | 17 | 5 | 3 |  |  | Owner | Create a new manager | Delegate management tasks to a pro
P&L | 18 | 5 | 8 |  |  | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy | Demonstrate the use of Java iterators with this feature
RTM | 19 | 5 | 8 |  |  | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members | Demonstrate the use of Java iterators with this feature
UD | 20 | 6 | 21 |  |  | Manager | Create unified dialogs across the application | Interact more efficiently with the program | Each command (e.g., Create > Donut) should required a single dialog
EF | 21 | 6 | 8 |  |  | Manager | Edit a product | Improve our data and keep it synced to reality
The Features below are BONUS work. If implemented, they will be graded, and the bonus awarded, at the end of Sprint 6
|  | Bonus |  |  |  | (If a Bonus feature changes AFTER you have implemented it, please notify the Professor ASAP)
PIX | 22 |  | 21 |  |  | Customer | Add and display pictures for each item | Better understand the menu | Pics would be added on product creation, and displayed when composing a new order
ASTO | 23 |  | 8 |  |  | Manager | Also associate a server with the order they fill | Keep track of our employee productivity
XT | 24 |  | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order, but keep their historical data) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 25 |  | 5 |  |  | Manager | Restore a server | Add a former team member tack into service
TIPS | 26 |  | 8 |  |  | Server | Calculate a percentage of each order served and report on each Server’s tips | Pay tip income as well as salary to Servers
AI | 27 |  | 8 |  |  | Server | Restock donuts and coffees | Ensure we can fill every order
MST | 28 |  | 5 |  |  | Manager | Manage the state of each order (unfilled -> filled and unpaid -> paid,, or unfilled / unpaid -> canceled) | Ensure each order is filled and payment collected | This is a good bonus problem if you attend the (optional) Lecture 24 on state machines
POS | 29 |  | 5 |  |  | Server | Show the products in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
RI | 30 |  | 5 |  |  | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
RO | 31 |  | 8 |  |  | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 32 |  | 5 |  |  | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
ROA | 33 |  | 3 |  |  | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
CENEW | 34 |  | 13 |  |  | Owner | Create a new franchise | Franchise my company
XI | 35 |  | 21 |  |  | Manager | Retire a product (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu